Part I. BASIC INFORMATION

| - Title of the Project |  |  |  | : | BOOSTING RESEARCH-BASED STARTUPS THROUGH DOST-SNSU WAVES TECHNOLOGY BUSINESS INCUBATOR |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| - Proponents |  |  |  | : | Project Leader: MS. STEPHINEJANE E. MUSICO (F) Associate Professor I Project Staff: DR. ARVIN E. MAG-USARA (M) Associate Professor V DR. ADRIANO V. PATAC, JR. (M) Professor III MS. MARY AMOR G. FIGUEROA (F) Associate Professor II ENGR. GRACECHELL M. PASCUA (F) Associate Professor I MS. PRINCES GRACE A. RETITA (F) Associate Professor IV MS. MILCAH B. CADAVIS (F) Instructor III |  |  |  |  |
| - Implementing Agency |  |  |  | : | SNSU – Main Campus |  |  |  |  |
| - Duration |  |  |  | : | 9 months |  |  |  |  |
| - Project Location |  |  |  | : | SNSU – City Campus |  |  |  |  |
| - Source of Fund |  |  |  | : | SNSU Local Research Funds |  |  |  |  |
| - Estimated Budget Requirement |  |  |  | : | Ᵽ 1,000,000.00 |  |  |  |  |
| - Socio-economic Impact |  |  |  | : | SDG 4. Quality Education: Offering entrepreneurial activities, workshops, and access to experts enables startups to enhance their technical, business, and leadership skills, promoting lifelong learning and skills development. SDG 8. Decent Work and Economic Growth: Foster entrepreneurship and innovation, providing mentorship, access to networks, funding, and business development resources for tech startups can stimulate economic growth and create employment opportunities. SDG 9. Industry, Innovation, and Infrastructure: A driving force for the development of sustainable infrastructure, the adoption of new technologies, and the creation of innovative solutions to global challenges. SDG 11. Sustainable Cities and Communities: Promotes sustainable business solutions that address urban and rural development challenges. SDG 12. Responsible Consumption and Production: Creation of sustainable business models and resource-efficient innovations. SDG 13. Climate Action: Advocating green technologies, renewable energy, and environmental solutions. SDG 17. Partnerships for the Goals: Act as hubs for collaboration, connecting entrepreneurs with industry experts, investors, and educational institutions, fostering a cooperative ecosystem that supports sustainable development goals. __________________________________________________ |  |  |  |  |
| - GAD Score |  |  |  | : | 17.00 ; Gender-responsive |  |  |  |  |
| - Relevance based on Identified Priority Agenda |  | NIBRA - Water Security - Food and Nutrition Security - Health Sufficiency ✔ Clean Energy ✔ Sustainable Communities - Inclusive Nation Building - Policy Research |  |  |  | AANR - Crops R&D Agenda - Livestock R&D Agenda - Forestry R&D Agenda ✔ Natural Resources & Environment R&D Agenda ✔ Climate Change Adaptation & Mitigation and Disaster Risk Reduction - Technology Transfer - Socio-Economics, Policy Research & Governance |  | HEALTH RESEARCH - Functional Food - Nutrition and Food Safety - Re-emerging and Emerging Diseases - Disaster Risk Reduction And Climate Change Adaptation In Health |  |  |
| - Responsiveness to Regional Development Plan |  |  | ✔ RDP Chapter Chapter 10 Advance Research and Development, Technology, and Innovation |  |  |  | Outcome Outcome 3: Technology adoption, utilization, and commercialization scaled-up Outcome 4: Innovation and entrepreneurship accelerated |  |
| - Responsiveness to Philippine Development Plan |  |  | PDP Chapter Chapter 8 Advance Research and Development, Technology, and Innovation |  |  |  | Outcome Outcome 3: Technology extension, adoption, utilization, and commercialization scaled-up Outcome 4: Innovation and entrepreneurship accelerated |  |

Part II. TECHNICAL DESCRIPTION

- RATIONALE/SIGNIFICANCE OF THE PROJECT

The DOST-SNSU WAVES Technology Business Incubator (TBI) has been established at Surigao del Norte State University (SNSU) through the DOST-PCIEERD's HEIRIT program. It provides support for technology-based startups emerging from the university's research and innovation ecosystem. The two-year project laid the foundation for setting up entrepreneurial awareness, supporting innovation, and forging partnerships and linkages.

DOST-SNSU WAVES TBI has demonstrated significant potential in promoting innovation and entrepreneurship within SNSU and the community during the first two years. This initial effort has laid a good foundation, evidenced by various activities and engagements that promote entrepreneurship and innovation. However, the culmination of HEIRIT funding might causes to disrupt this promising momentum and jeopardize the long-term sustainability of the TBI. Continued operation is essential to build on the established infrastructure, expertise, and network, ensuring continued support for promising startups, driving regional economic development, and fulfilling SNSU's commitment to innovation. This proposal seeks university support to bridge the funding gap and secure the TBI's future as a vital program for technological advancement and economic growth.

Tel. Nos.: (086) 816-0026						       		                Email: info@snsu.edu.ph

URL: snsu.edu.ph

Tel. Nos.: (086) 816-0026						       		                Email: info@snsu.edu.ph

URL: snsu.edu.ph

- OBJECTIVES OF THE PROJECT

#### General Objective

#### To promote innovation, entrepreneurship, and economic development by providing comprehensive support and resources to startups and spin-off companies emerging from the university, facilitating the translation of research and ideas into successful businesses, strengthening the university's role as a catalyst of innovation, and ensuring the operational continuity of the DOST-SNSU WAVES Technology Business Incubator (TBI) through securing necessary funding, resources, and institutional support, enabling it to effectively nurture startups, drive innovation, contribute to regional economic development, and enhance the university's role as a center for technological advancement and entrepreneurial activity.

#### Specific Objectives

- Promote technopreneurship and startup culture by supporting the development of research-based ventures;

- Establish strategic partnership and create an environment to support startup development;

- Deliver a comprehensive incubation program; and

- Commercialize startup/spinoff technologies.

- REVIEW OF LITERATURE

### Research-based Startups

### Translating university research into successful startups is crucial for innovation and economic growth, but research-based ventures face unique challenges.  They often require longer development timelines, significant capital investment, and effective strategies to bridge the gap between academic findings and market needs.  Recent literature highlights the importance of targeted support, including access to seed funding and venture capital, which is often critical for these capital-intensive ventures (Block et al., 2017). Specialized incubators and accelerators designed for deep tech startups are vital for connecting researchers with investors who understand their technologies (Clarysse et al., 2019).  Mentorship from experienced entrepreneurs and industry experts is also essential for navigating the complexities of building a business around research (Shane & Stuart, 2019).

### Beyond funding and mentorship, access to specialized facilities and equipment, often provided by university-affiliated incubators, is crucial for research-based startups, especially in fields like biotechnology.  These resources reduce initial capital expenditure and accelerate development.  Furthermore, maintaining a strong connection to the university research ecosystem is vital.  This includes facilitating access to research expertise, licensing intellectual property, and fostering collaborations with faculty (Etzkowitz & Leydesdorff, 2000).  By providing this comprehensive support, universities can effectively nurture research-based startups and maximize their potential for success.

### The Importance of University-Based TBIs

### University-based technology business incubators have emerged as vital components of the innovation ecosystem, playing an important role in advocating entrepreneurship, driving technological advancement, and contributing to regional economic development.  These incubators leverage the resources and intellectual capital of universities to nurture startups and translate research into marketable products and services.  A key strength of TBIs lies in their ability to provide a supportive environment for nascent ventures, offering access to mentorship from experienced faculty and entrepreneurs, cutting-edge research facilities, and a network of potential investors and partners (Powers & McDougall, 2005).  This access to resources significantly increases the survival rate of startups compared to those operating independently (Shane, 2004).

### Furthermore, TBIs contribute to the university's core mission of teaching and research by providing students with hands-on experience in entrepreneurship and commercializing research findings (Etzkowitz & Leydesdorff, 2000).  Students gain valuable skills in business development, marketing, and finance, enhancing their employability and entrepreneurial potential.  TBIs also facilitate the transfer of technology from the university to the marketplace, bridging the gap between academic research and practical application.  By fostering spin-off companies and attracting industry partnerships, TBIs enhance the university's reputation as a center for innovation and contribute to its economic impact on the surrounding community.  In essence, TBIs serve as a critical link between academia, industry, and the entrepreneurial ecosystem, promoting a dynamic environment for innovation and economic growth.

TBI in Promoting Innovation and Entrepreneurship

Technology business incubators (TBIs) play a key role in supporting innovation and entrepreneurship by providing a structured environment and resources to support the growth of early-stage startups. These incubators function as catalysts, bridging the gap between innovative ideas and successful businesses. They offer a range of services, including mentorship, business development training, access to funding, networking opportunities, and shared office space, all designed to increase the chances of startup survival and success (Hackett & Dilts, 2004). By mitigating the risks associated with early-stage ventures, TBIs encourage individuals to pursue entrepreneurial endeavors and translate innovative concepts into viable products and services.

TBIs contribute to the innovation ecosystem by nurturing a culture of entrepreneurship and facilitating the commercialization of modern technologies. They provide a platform for entrepreneurs to connect with potential investors, partners, and customers, fostering collaboration and knowledge sharing (Colombo & Delmastro, 2002). Furthermore, TBIs often focus on specific industries or technologies, creating specialized ecosystems that foster innovation within those sectors. This specialization allows incubators to tailor their services to the specific needs of startups in those areas, maximizing their impact.

The impact of TBIs extends beyond individual startups, contributing to regional and national economic development. Successful startups create jobs, generate revenue, and attract further investment, stimulating economic growth and enhancing competitiveness (Audretsch et al., 2006). TBIs, therefore, serve as vital engines for innovation and entrepreneurship, driving economic growth and fostering a more dynamic and competitive business environment.

TBI in Addressing the Sustainable Development Goals

Technology business incubators (TBIs) are increasingly crucial for achieving the Sustainable Development Goals (SDGs). Beyond supporting general startup growth, many TBIs now prioritize ventures addressing specific societal and environmental challenges aligned with the SDGs (UNCTAD, 2019). These "impact incubators" provide tailored support to businesses with social or environmental missions, helping them develop scalable solutions. TBIs contribute to various SDGs, from clean energy (SDG 7 & 13) to sustainable agriculture (SDG 2 & 12) (WEF, 2017). They accelerate innovation by providing resources, mentorship, and networks to startups tackling SDG-related issues. Furthermore, TBIs fosters inclusive growth (SDG 8) by supporting job-creating, sustainable businesses and empowering marginalized communities through social enterprises. TBIs translate the SDGs into tangible actions and impactful solutions.

- METHODOLOGY

This section outlines the strategies and activities that will be undertaken to achieve the objectives of the SNSU WAVES Technology Business Incubator (TBI).

- Promote technopreneurship and startup culture in the university.

Entrepreneurial and startup awareness campaigns will be conducted across all four SNSU campuses, targeting faculty and students in research and entrepreneurship-related courses. These campaigns will utilize workshops and seminars covering topics such as startup basics, ideation, and pitch training, among others, to promote a vibrant technopreneurial culture.

- Establish strategic partnerships to support startup development.

Potential partners from industry, government, academe, and the investment community will be identified and prioritized. Relationship-building activities, including meetings and networking events, will be conducted to secure partnerships. Formal agreements will be established with partners, outlining roles, responsibilities, and resource contributions to support incubated startups.

- Deliver a comprehensive incubation program.

The SURF incubation program designed by WAVES TBI will be implemented to the incubated startups. The student startup teams formed from the research/capstone and entrepreneurship courses will be recruited to on-board with the program. Experienced mentors will also be on-boarded and trained to provide guidance. Regular workshops and training sessions, led by experts, will supplement the core curriculum.

- Commercialize startup technologies.

Promising innovations will be commercialized through tailored commercialization strategies. The startups will then be provided with essential resources, mentorship, and project management support, while promoting strategic partnerships and monitoring key performance indicators to ensure successful market entry and growth.

- PROJECT PERSONNEL

      - TBI Manager a faculty designated who will manage the day-to-day operations of the office. He will oversee the implementation of the project and ensure timely accomplishments of targets and deliverables. He will lead the team in the planning, implementation, monitoring and evaluation of programs and other key activities under the project.

      - Project Staff a faculty members designated to aid the TBI Manager in the delivery of project targets.

      - Project Technical Assistant (PTA) or the Startup Specialist will focus on facilitating and monitoring of startups under the incubation program. The PTA will develop and implement monitoring and evaluation systems to track the progress of startups. He/she will also collaborate with mentors and network with other startup enablers, expanding TBI’s network.

      - Administrative Staff will provide logistical and administrative support to the organization and undertake relevant duties and tasks as may be required.

- LIST OF REFERENCES

- Audretsch, D. B., Feldman, M. P., & Link, A. N. (2006). Entrepreneurship and the knowledge economy. Oxford University Press.

- Block, J. H., Colombo, M. G., Cumming, D. J., & Vismara, S. (2017). Journal of Corporate Finance, 48, 584-606.

- Clarysse, B., Wright, M., Bruneel, J., & Mahajan, A. (2019). Technovation, 80-81, 2-18.

- Colombo, M. G., & Delmastro, S. (2002). How do technology incubators affect firm performance? Journal of business venturing, 17(4), 355-373.

- Etzkowitz, H., & Leydesdorff, L. (2000). Research policy, 29(2), 213-233.

- Etzkowitz, H., & Leydesdorff, L. (2000). The dynamics of innovation: From National Systems to a Triple Helix of university-industry-government relations. Research policy, 29(2), 213-233.

- George, G., & Bock, A. J. (2011). The business model in practice and its implications for entrepreneurs. Entrepreneurship theory and practice, 35(1), 83-111. (While this reference isn't directly about SDGs, it provides a crucial foundation for understanding how business models are adapted for social impact, which is essential for the SDG-focused work of TBIs).

- Hackett, S. M., & Dilts, D. M. (2004). A systematic review of business incubation research. Journal of Technology Transfer, 29, 55-73.

- Powers, J. B., & McDougall, P. P. (2005). University start-up formation and technology licensing: A resource-based perspective. Journal of Business Venturing, 20(4), 487-502.

- Shane, S. A. (2004). Academic entrepreneurship: University spinoffs and wealth creation. Edward Elgar Publishing.

- Shane, S. A., & Stuart, T. E. (2019). Technology strategy. Cambridge University Press.

- UNCTAD (2019). Technology and innovation report 2019: Strengthening innovation for sustainable development. United Nations Conference on Trade and Development.

- WEF (2017). The Fourth Industrial Revolution and sustainable development. World Economic Forum.

- GANTT CHART

| OBJECTIVES/ TARGETS | ACTIVITIES | MONTHS |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| - Promote technopreneurship and startup culture by supporting the development of research-based ventures | - Conduct awareness campaign activities to students taking up research and entrepreneurship courses. |  |  |  |  |  |  |  |  |  |
|  | - Conduct startup basics and pitch training to student founders. |  |  |  |  |  |  |  |  |  |
| - Establish strategic partnership and create an environment to support startups development | - Conduct reverse pitching and ideation sessions (Design Thinking) |  |  |  |  |  |  |  |  |  |
|  | - Conduct startup bootcamp |  |  |  |  |  |  |  |  |  |
|  | - Conduct pitching competition within the i2FAME agenda of Caraga |  |  |  |  |  |  |  |  |  |
|  | - Conduct stakeholders/ consultative forum with partner institution and mentors |  |  |  |  |  |  |  |  |  |
| - Deliver a comprehensive incubation program | - Conduct mentorship activities for startups enrolled in the incubation program. |  |  |  |  |  |  |  |  |  |
|  | - Validate prototypes and endorse for IP protection application. |  |  |  |  |  |  |  |  |  |
| - Commercialize startup/spinoff technologies. | - Conduct demo day |  |  |  |  |  |  |  |  |  |
|  | - Forge commercialization agreement with technology/ product adopter. |  |  |  |  |  |  |  |  |  |

- MECHANICS

| OBJECTIVES/ TARGETS | ACTIVITIES | INDICATORS | TARGETS |
| --- | --- | --- | --- |
| - Promote vibrant technopreneurship and startup culture by supporting the development of research-based ventures | - Conduct awareness campaign activities. | Active participation of the students (including freshmen & returnees) | 300 students (dis-aggregated by sex) from across four SNSU Campuses. |
|  | - Conduct Startup Basics and Pitch Training. | Endorsement of startup teams from their mentors | 100 students (dis-aggregated by sex) from across four SNSU Campuses. |
| - Establish strategic partnership and create an environment to support startups development | - Conduct reverse pitching and ideation sessions (Design Thinking). | Endorsement of startup teams from their mentors | 80 students and faculty (dis-aggregated by sex) from across four SNSU Campuses. |
|  | - Conduct startup bootcamps | Endorsement of startup teams from their mentors | 50 students and faculty (dis-aggregated by sex) from across four SNSU campuses. |
|  | - Conduct pitching competition within the i2FAME agenda of Caraga | Startup entries aligned within the i2FAME agenda. | 5 startups (dis-aggregated by sex) enrolled in the Incubation Program. |
|  | - Conduct stakeholders/ consultative forum with partner institution and mentors | Number of MOU/MOA, and contracts signed | 5 MOU/MOA and 5 mentor contracts signed. |
| - Deliver a comprehensive incubation program | - Conduct mentorship activities for startups enrolled in the incubation program. | Number of startups receiving mentorship support. | Product Launching |
|  | - Validate prototypes and endorse for IP protection application. | Number of endorsed patent applications through ITSO. | 2 products submitted for IP protection |
| - Commercialize startup/spinoff technologies. | - Conduct demo day | Number of demo day conducted | 1 demo day conducted with potential investors |
|  | - Forge commercialization agreement with technology/product adopter. | Number of signed commercialization agreement | 4 commercialization agreements finalized – 1 from each campus. |

- LINE-ITEM BUDGET

| PARTICULARS | BUDGET NEEDED |
| --- | --- |
| MOOE EXPENSES |  |
| Travel Expenses (Per diem, and other travel expenses) | 200,000.00 |
| Supplies and Materials Expenses |  |
| Office Supplies | 45,475.00 |
| Training Expenses (Meetings, Ideations, Hackathons, Pitching Competitions, etc.) | 455,000.00 |
| Representation Expenses | 60,000.00 |
| Other MOOE | 25,525.00 |
| Printing and Publication Expenses | 29,000.00 |
| Other General Services |  |
| One (1) Job Order (15,000.00/mo X 5 months) | 75,000.00 |
| Other Professional Services |  |
| One (1) Project Technical Assistant (22,000.00/mo X 5 months) | 110,000.00 |
| Total | Ᵽ 1,000,000.00 |

Prepared by:

STEPHINEJANE E. MUSICO

Project Proponent

Recommending Approval:

RUEL T. BUBA

Research Director

Concurred by:

RONITA E. TALINGTING, PhD

Campus Director

SNSU City Campus

Approved by:

ROMY JUN A. SUNICO, DTE

Vice President for Research, Innovation

and Extension

GENDER AND DEVELOPMENT COMBINED GENERIC CHECKLISTS

FOR PROJECT IDENTIFICATION AND DESIGN

| PROJECT TITLE: | BOOSTING RESEARCH-BASED STARTUPS THROUGH DOST-SNSU WAVES TECHNOLOGY BUSINESS INCUBATOR |  |  |  |
| --- | --- | --- | --- | --- |
| PROJECT NUMBER (IF APPLICABLE) |  |  |  |  |
| ESTIMATED COST: | Ᵽ 1,000,000.00 |  |  |  |
| DEPARTMENT / UNIT / COLLEGE | RIE / WAVES TBI Center |  |  |  |
| PROJECT LEADER | MS. STEPHINEJANE E. MUSICO |  |  |  |
| PROJECT MEMBER / PROPONENT: | NAME: | OFFICE / DEPARTMENT / COLLEGE | CONTACT # | EMAIL ADRESS/ES |
|  | 1. Ms. Stephinejane E. Musico (F) | CITY CAMPUS |  | smusico@ssct.edu.ph |
|  | 2. Dr. Arvin E. Mag-usara (M) | CITY CAMPUS |  | amagusara@ssct.edu.ph |
|  | 3. Dr. Adriano V. Patac, Jr. (M) | CITY CAMPUS |  | apatac@ssct.edu.ph |
|  | 4. Ms. Mary Amor G. Figueroa (F) | MAINIT CAMPUS |  | mafigueroa03@gmail.com |
|  | 5. Engr. Gracechell M. Pascua (F) | CITY CAMPUS |  | gpascua@ssct.edu.ph |
|  | 6. Ms. Princess Grace A. Retita (F) | CITY CAMPUS |  | pretita@ssct.edu.ph |
|  | 7. Ms. Milcah B. Cadavis (F) | CITY CAMPUS |  | mcadavis@ssct.edu.ph |
| PROJECT DURATION: | 11 months | PROJECT LOCATION: | City Campus |  |
| DESCRIPTION: | The DOST-SNSU WAVES Technology Business Incubator (TBI) has been established at Surigao del Norte State University (SNSU) through the DOST-PCIEERD's HEIRIT program. It provides support for technology-based startups emerging from the university's research and innovation ecosystem. The two-year project laid the foundation for setting up entrepreneurial awareness, supporting innovation, and forging partnerships and linkages. DOST-SNSU WAVES TBI has demonstrated significant potential in promoting innovation and entrepreneurship within SNSU and the community during the first two years. This initial effort has laid a good foundation, evidenced by various activities and engagements that promote entrepreneurship and innovation. However, the culmination of HEIRIT funding might causes to disrupt this promising momentum and jeopardize the long-term sustainability of the TBI. Continued operation is essential to build on the established infrastructure, expertise, and network, ensuring continued support for promising startups, driving regional economic development, and fulfilling SNSU's commitment to innovation. This proposal seeks university support to bridge the funding gap and secure the TBI's future as a vital program for technological advancement and economic growth. |  |  |  |

Instruction: Put a check in the appropriate column to signify the degree to which a project proponent has accomplished with each GAD criterion. Under column 2a if nothing has been done; under column 2b if the element, item, or question has been partly accomplished; and column 2c if the item has been fully complied with.

(PLEASE SEE ATTACHED GUIDE FOR ACCOMPLISHING THE CHECKLIST)

| Element and item/question (Column 1) | Done? (Column 2) |  |  | *Score for an item/element (Column 3) | Evidence/s |
| --- | --- | --- | --- | --- | --- |
|  | No 2a | Partly 2b | Yes 2c |  |  |
| 1.0 Involvement of women and men (max score: 2; for each item, 1) |  |  |  | 2 |  |
| 1.1 Participation of women and men in beneficiary groups in problem identification (possible scores: 0, 0.5, 1.0) |  |  | / |  | B. Proponents- which shows the participation of women and men in the project |
| 1.2 Participation of women and men in beneficiary groups in project design (possible scores: 0, 0.5, 1.0) |  |  | / |  | Proponents Gantt Chart where target participants will be dis-aggregated by sex |
| 2.0 Collection of sex-disaggregated data and gender-related information (possible scores: 0, 1.0, 2.0) |  |  | / | 2 | Gantt Chart where target participants will be dis-aggregated by sex |
| 3.0 Conduct of gender analysis and identification of gender issues (max score: 2; for each item, 1) |  |  |  | 1 |  |
| 3.1 Analysis of gender gaps and inequalities related to gender roles, perspectives and needs, or access to and control of resources (possible scores: 0, 0.5, 1.0) |  | / |  |  | Rationale |
| 3.2 Analysis of constraints and opportunities related to women and men’s participation in the project (possible scores: 0, 0.5, 1.0) |  | / |  |  | Rationale |
| 4.0 Gender equality goals, outcomes, and outputs (possible scores: 0, 1.0, 2.0) Does the project have clearly-stated gender equality goals, objectives, outcomes or outputs? |  |  | / | 2 |  |
| 5.0 Matching of strategies with gender issues (possible scores: 0, 1.0, 2.0) Do the strategies and activities match the gender issues and gender equality goals identified? |  |  | / | 2 |  |
| 6.0 Gender analysis of likely impacts of the project (max score: 2; for each item, 0.67) |  |  |  | 2 |  |
| 6.1. Are women and girl children among the direct or indirect beneficiaries? (possible scores: 0, 0.33, 0.67) |  |  | / |  |  |
| 6.2. Has the project considered its long-term impact on women’s socioeconomic status and empowerment? (possible scores: 0, 0.33, 0.67) |  |  | / |  |  |
| 6.3. Has the project included strategies for avoiding or minimizing negative impacts on women’s status and welfare? (possible scores: 0, 0.33, 0.67) |  |  | / |  |  |
| 7.0 Monitoring targets and indicators (possible scores: 0, 1.0, 2.0) Does the project include gender equality targets and indicators to measure gender equality outputs and outcomes? |  | / |  | 1 |  |
| 8.0. Sex-disaggregated database requirement (possible scores: 0, 1.0, 2.0) Does the project M&E system require the collection of sex-disaggregated data? |  | / |  | 1 |  |
| 9.0. Resources (max score: 2; for each question, 1) |  |  |  | 2 |  |
| 9.1. Is the budget allotted by the project sufficient for gender equality promotion or integration? OR, will the project tap counterpart funds from LGUs/partners for its GAD efforts? (possible scores: 0, 0.5, 1.0) |  |  | / |  |  |
| 9.2. Does the project have the expertise to promote gender equality and women’s empowerment? OR, is the project committing itself to invest project staff time in building capacities within the project to integrate GAD or promote gender equality? (possible scores: 0, 0.5, 1.0) |  |  | / |  |  |
| 10. Relationship with the agency’s GAD efforts (max score: 2; for each question or item, 0.67) |  |  |  | 2 |  |
| 10.1 Will the project build on or strengthen the agency/NCRFW/ government’s commitment to the empowerment of women? (possible scores: 0, 0.33, 0.67) IF THE AGENCY HAS NO GAD PLAN: Will the project help towards the formulation of the implementing agency’s GAD plan? |  |  | / |  |  |
| 10.2. Will it build on the initiatives or actions of other organizations in the area? (possible scores: 0, 0.33, 0.67) |  |  | / |  |  |
| 10.3 Does the project have an exit plan that will ensure the sustainability of GAD efforts and benefits? (possible scores: 0, 0.33, 0.67) |  |  | / |  |  |
| TOTAL GAD SCORE FOR PROJECT DEVELOPMENT STAGE |  |  |  | 17 | Gender-responsive |

Source: Harmonized Gender and Development Guidelines for Project Development. Implementation. Monitoring and Evaluation.  Second Edition, Third Printing. National Economic and Development Authority. Philippine Commission on Women. Official Development Assistance Gender and Development Network. Pp 21-22

Interpretation of the GAD score

0 - 3.9 GAD is invisible in the project (proposal is returned).

4.0 - 7.9 Proposed project has promising GAD prospects (proposal earns a "conditional pass," pending identification of gender issues and strategies and activities to address these and inclusion of the collection of sex-disaggregated data in the monitoring and evaluation plan).

8.0 - 14.9 Proposed project is gender-sensitive (proposal passes the GAD test)

15.0 - 20.0 Proposed project is gender-responsive (proponent is commended)

Checked by:

MS. STEPHINEJANE E. MUSICO				_________________________

Signature over Printed Name of the Evaluator			Date Evaluated

Verified by:

ENGR. GRACECHELL M. PASCUA				_________________________

Signature over Printed Name of the Evaluator			Date Evaluated